## CDSP
Project ID/Project Name:
Contractor:
Work Description:
Quality Document Submittal Plan
Contractor/ QC Submittal | [8 empty] | QA Review
Submittal Description | Submittal Frequency | Timing of Submittal | Submittal Type | In-process Storage Location | Folder Location | Document Submittal Date |  |  | QA Responsibility | Folder Location
[5 empty] | ● Provide hyperlink to folder in PIMS Partner Center ● Folders shall only contain items identified per the folder naming structure ● Consult T&PS Construction Quality for file naming requirements ● File paths are limited to 400 characters | One Time Submittals | On-Going Submittals |  | If secondary documentation storage is required after a QA review, designate which group is responsible: T&PS or CQA Firm | ● Provide hyperlink to folder in PIMS for Final file location. ● Folders shall only contain items identified per the folder naming structure ● Consult T&PS Construction Quality for file naming requirements ● File paths are limited to 400 characters
[6 empty] | Submittal Date | Submittal Start Date | Final Submittal Date
General
Nonconformance Report (NCR) | As Needed | Within 7 days of nonconforming event | NCR | NCR
QA Manual - Site Specific | One time - Update as required | Within 5 Days of Contract Award | CMC | Partner
Calibration Certification | Updated throughout project | As certs expire or arrive onsite | CMC | Partner
Calibration Log | Updated throughout project | As certs expire or arrive onsite | Partner | Partner
Inspection and Test Plans | One time - Update as required | 14 days prior to performing work | CMC | Partner
Contractor QC Manager Resume / Certifications | One time - Update as required | 14 days prior to performing work | CMC | Partner
Contractor Quality Surveillance Plan | Updated throughout project | Prior to status update meetings or minimum 2 per month | Partner | Partner
Third Party Testy Agency Resumes / Certifications | One time - Update as required | 14 days prior to performing work | CMC | Partner
Quality Verification Reports | As outlined in ITP | Within 7 days of reporting event | Partner | Partner
Contractor Requests For Clarification | As Needed | Throughout project | RFI | RFI
Tensiometer Calibration | Per Year | 14 Days prior to installation | CMC | Partner
Daily Reports | Daily | As required in contract special conditions - No later than As required in contract special conditions - 9:30am the following day | Partner | Partner
Weekly Reports | Weekly | As required in contract special conditions - No later than Tuesday 9:30am on following week | CMC | Partner
Monthly Reports | Monthly | As required in contract special conditions - 5th of each month | CMC | Partner
Annual Reports | Annually | As required in contract - By January 31st of Each Year | CMC | Partner
Final Certification Report | One Time | Within 15 days of completion of construction activities. | CMC | Partner
Construction Quality Surveillance Plan (CQSP) | One time - Update as required | Prior to start of quality related work | CMC | Partner
Survey
Surveyor Certs | One time - Update as required | 14 days before surveying begins | CMC | Partner
Survey Instrument Calibration | Updated throughout project | As certs expire or arrive onsite | CMC | Partner
Record drawing of benchmarks and control points | One time - Update as required | 14 days before surveying begins | CMC | Partner
Initial record survey, prior to beginning earthmoving | One time - Update as required | 14 days before surveying begins | CMC | Partner
Intermediate record survey drawings | One time - Update as required | As soon as practicable - Prior to install of subsequent layer | CMC | Partner
Survey Control Network | One time - Update as required | 14 days prior to use | CMC | Partner
Survey (as-builts and quantities) | One time - Update as required | As soon as practicable - Prior to install of subsequent layer | Partner | Partner
Welding
Nondestructive Test Procedures | One time - Update as required | Prior to performing NDE | CMC | Partner
Nondestructive Test Reports | As required | Within 7 day of NDE examination | Partner | Partner
Weld Procedures | One time - Update as required | Prior to commencement of welding activities (HDPE or Metal) | RFI | Partner
Weld Reject Rate Report | Weekly | As required in contract special conditions - No later than Tuesday 9:30am on following week | Partner | Partner
Material Certifications | Updated throughout project | Prior to use onsite | Partner | Partner
Heat Treating Procedures, Special Process Procedures | One time - Update as required | Prior to performing Heat Treating or Special Processes | CMC | Partner
Weld Map | Updated throughout project | Within a week of completion | Partner | Partner
3rd Party CWI Certs and Resumes | One time - Update as required | Prior to welding onsite | CMC | Partner
Welder Certifications | One time - Update as required | Prior to welding onsite | CMC | Partner
HDPE Pipe
HDPE ITP | One time - Update as required | Prior to commencement of welding activities (HDPE or Metal) | CMC | Partner
Material Certifications | Updated throughout project | Prior to use onsite | Partner | Partner
Weld Map | Updated throughout project | Within a week of completion | Partner | Partner
Bonder Certifications | One time - Update as required | Prior to welding onsite | CMC | Partner
HDPE Pipe - QC Certs and Resin Info, Installation Info, Calibration Info. | One time - Update as required | 14 days prior to shipment to site | Partner | Partner
Mechanical
Pipe Pressure Testing Documentation | As required | Within 7 days of testing event | Partner | Partner
Pipe - QC Certs and Resin Info, Installation Info, Calibration Info. | One time - Update as required | 14 days prior to shipment to site | Partner | Partner
Pipes/Fittings/Valves - Shop Drawings of all pipes, fittings, valves, appurtenances, etc. | One time - Update as required | 14 days prior to ordering materials. | Partner | Partner
Pipes/Fittings/Valves - Materials List and Suppliers | One time - Update as required | 14 days prior to ordering materials. | Partner | Partner
Pipes/Fittings/Valves - Pressure Testing Plan | One time - Update as required | 14 days prior to ordering materials. | Partner | Partner
Pipes/Fittings/Valves - Supplier Information | One time - Update as required | 14 days prior to ordering materials. | Partner | Partner
Pump Electrical Hookup Locations | One time - Update as required | 14 days after notice to proceed | Partner | Partner
Pumps - Materials, Manufactures, Shop Drawings, Models, Layout and diagrams, control panels, testing/commissioning plans, calibration records, etc. | One time - Update as required | 14 days prior to ordering materials. | Partner | Partner
Pumps - O&M Manuals | One time - Update as required | 14 days after completion of installation. | CMC | Partner
Pumps - As-builts and Redlines | One time - Update as required | As soon as practicable | CMC | Partner
Electrical
Electrical Torque Records | As required | Within 7 days of event | CMC | Partner
Megger Testing Records | As required | Within 7 days of event | CMC | Partner
Hi-Pot Test Records | As required | Within 7 days of event | CMC | Partner
PDMS Pull Cards | As required | Within 7 days of event | CMC | Partner
Coatings
Coatings Quality Form | One time - Update as required | 14 days before coating begins | CMC | Partner
Daily Completed Coatings Quality Inspection Form | Daily | As required in contract special conditions - No later than As required in contract special conditions - 9:30am the following day | Partner | Partner
Concrete
Concrete Pour Cards | As required | Signature required 24 hours prior to placement. Placed in PIMS within a week of placement | Partner | Partner
Grout Pour Cards | As required | Signature required 24 hours prior to placement. Placed in PIMS within a week of placement | Partner | Partner
Concrete Truck Tickets | One time - Update as required | Within 7 days of event | Partner | Partner
Rebar shop drawings (schedule, bar size, etc.) | One time - Update as required | 14 days prior to use | CMC | Partner
Concrete Mix Designs | One time - Update as required | 14 days prior to use | RFI | Partner
Concrete Supplier Certification | One time - Update as required | 14 days prior to use | CMC | Partner
Shop drawings for precast structures | One time - Update as required | 14 days prior to use | CMC | Partner
Shop drawings for spillway riser bases | One time - Update as required | 14 days prior to use | CMC | Partner
Hot/Cold Weather Concrete procedures | One time - Update as required | 14 days prior to use | RFI | Partner
Concrete formwork design | One time - Update as required | 14 days prior to use | CMC | Partner
List of concrete equipment, tools, construction means, etc. | One time - Update as required | 14 days prior to use | Partner | Partner
Concrete Structures - As-built Survey | One time - Update as required | As soon as practicable | CMC | Partner
Aggregate Source | One time - Update as required | 14 days prior to use | CMC | Partner
Aggregate Provider's production methods | One time - Update as required | 14 days prior to use | Partner | Partner
Aggregate Provider Certification | One time - Update as required | 14 days prior to use | CMC | Partner
Manufactured Liner
HDPE Liner Certifications | One time - Update as required | 14 days before shipment | CMC | Partner
HDPE Liner Installer Certifications | One time - Update as required | 14 Days prior to installation | CMC | Partner
HDPE Liner Destructive Test Results | Ongoing | within 7 days after completion | Partner | Partner
Closure Turf Installer Certifications | After production completion | 14 days before shipment | CMC | Partner
HDPE Liner / Closure Turf Third Party QC Inspector Certs | Prior to performing inspection |  | CMC | Partner
Manufacturers Certs: GCL Backed HDPE, resin, welding rod | One time - Update as required | 14 days before production begins | CMC | Partner
GSE Stud liner Certs: | One time - Update as required | 14 days before production begins | CMC | Partner
Manufacturers Certs: GSE Nonwoven fabric | One time - Update as required | 14 days before production begins | CMC | Partner
List of Geosynthetic Manufacturers qualifications | One time - Update as required | 14 days before production begins | CMC | Partner
Geomembrane Panel Deployment Log | Ongoing during deployment | Update weekly | Partner | Partner
Geomembrane Trial Seam Log | Ongoing during deployment | Update weekly | Partner | Partner
Geomembrane Fusion Seaming Log | Ongoing during deployment | Update weekly | Partner | Partner
Geomembrane Extrusion Seaming Log | Ongoing during deployment | Update weekly | Partner | Partner
Geomembrane Defect and Repairs Log | Ongoing during deployment | Update weekly | Partner | Partner
Survey as-built of top of Geomembrane | One time - Update as required | As soon as practicable | Partner | Partner
Survey as-built of top of Sand Fill | One time - Update as required | As soon as practicable | Partner | Partner
Proposed Panel Layout | One time - Update as required | 14 days prior to install | CMC | Partner
Final Topographic Survey | At end of each certifiable layer | As soon as practicable | Partner | Partner
Liner Warranty | One time - Update as required | 14 days after completion of installation. | CMC | Partner
Liner As-built Drawing(s) - panels, seams, repairs, destructs, etc. | After each installation period. A final as- built will be submitted at the end of the job, but submitting and checking intermittent section of liner as they are completed is a much better method of operation and ensures that any errors do not transmit through the entire job. | As soon as practicable | CMC | Partner
GDN Manufacturer Info (name, product name, history, experience, MARV specs.) | One time - Update as required | 14 days prior to manufacturing | Partner | Partner
Closure Turf - MQC Data, Manufacturer's Certs., and Installation Info | One time - Update as required | 14 days prior to transport of materials. | Partner | Partner
Closure Turf Infill - Source, Manufacturer's Info and Methods, Procedures, Installation Info, and Prequalification testing. | One time - Update as required | 14 days prior to transport of materials. | Partner | Partner
Closure Turf As-built (Extents) | After each installation period. A final as- built will be submitted at the end of the job, but submitting and checking intermittent section of liner as they are completed is a much better method of operation and ensures that any errors do not transmit through the entire job. | As soon as practicable | Partner | Partner
Geomembrane Certification Info (certs, history, resin, MARV, etc.) | One time - Update as required | 21 Days prior to producing geomembrane | Partner | Partner
Geomembrane Resin Information | One time - Update as required | 14 days prior to producing geomembrane | Partner | Partner
Geomembrane MQC Data (and seaming procedures) | One time - Update as required | 14 days prior to shipment to site | Partner | Partner
Structural Fill
Structural Fill: Proctor (1/5000 cy min.) | Ongoing during subgrade installation | Within 7 days of testing event | CMC | Partner
Clay Screened Fill: Proctor (1/5000 cy min.) | Ongoing during subgrade installation | Within 7 days of testing event | CMC | Partner
Subgrade Proof Roll Acceptance and Map of Area | Prior to placement of compacted fill (Acceptance happens in the field) | Within 7 days of testing event | Partner | Partner
Structural Fill Density Test Summary | Ongoing during subgrade installation | Update and report weekly | Partner | Partner
Structural Fill Density Test Grid | One time - Update as required | Within 7 days of testing event | Partner | Partner
Clay Screened Fill Density Test Summary | Ongoing during subgrade installation | Update and report weekly | Partner | Partner
Clay Screened Fill Density Test Grid | One time - Update as required | Within 7 days of testing event | Partner | Partner
Clay Screened Fill Subgrade Acceptance | One time - Update as required | Within 7 days of testing event | Partner | Partner
Survey As-built Top of Structural Fill | One time - Update as required | As soon as practicable | Partner | Partner
Survey As-built Top of Clay Screened Fill | One time - Update as required | As soon as practicable | Partner | Partner
Anchor Trench Density Test Summary | Ongoing during subgrade installation | Update and report weekly | Partner | Partner
Anchor Trench Density Test Grid | One time - Update as required | Within 7 days of testing event | Partner | Partner
GAB Fill Density Test Summary | Ongoing during subgrade installation | Update and report weekly | Partner | Partner
GAB Fill Density Test Grid | One time - Update as required | Within 7 days of testing event | Partner | Partner
Subgrade Acceptance Forms | Subgrade to be approved daily in the field by all parties, but all subgrade acceptance forms should be submitted as a packet at the end of the installation period. | As soon as practicable | Partner | Partner
Earthwork - Equipment/Materials List, Construction Means, Location of Jack/Bore Pits, Dewatering Method | One time - Update as required | 45 days before start of activities | Partner | Partner
Jack/Bore Installer - History and Documentation | One time - Update as required | 45 days before start of activities | Partner | Partner
Offsite Borrow Source Material(s) | One time - Update as required | 14 days prior to importing materials | Partner | Partner
Slurry/One Pass Wall
Slurry Trench - Contractor Qualifications | One time - Update as required | 14 days before production begins | Partner | Partner
Slurry Trench - Work Plan | One time - Update as required | 14 days before production begins | Partner | Partner
Slurry Trench - Statements (Test Reports, Field Test Reports, Certificates) | One time - Update as required | Within 7 days of testing event | Partner | Partner
Slurry Trench - Post Construction Completion Report | One time - Update as required | 30 days after Slurry Wall installation is complete | Partner | Partner
Slurry Trench - As-built Profile | One time - Update as required | 30 days after Slurry Wall installation is complete | Partner | Partner
One-Pass Walls - Contractor Qualifications | One time - Update as required | 14 days before production begins | Partner | Partner
One-Pass Walls - Work Plan | One time - Update as required | 14 days before production begins | Partner | Partner
One-Pass Walls - Statements (Test Reports, Field Test Reports, Certificates) | One time - Update as required | Within 7 days of testing event | Partner | Partner
One-Pass Walls - Post Construction Completion Report | One time - Update as required | 30 days after One-Pass Wall installation is complete | Partner | Partner
One-Pass Walls - As-built Profile | One time - Update as required | 30 days after One-Pass Wall installation is complete | Partner | Partner
Revision History Table
Date | Revision (CMC Number) | Description of Change